## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Data Loading & Cleaning - Remove duplicates and handle missing values | 1 | 1 | Load the TATA Retail dataset into the system to initiate the data exploration and preprocessing phases of the machine learning workflow. | MUST HAVE | Data Source Availability(Kaggle), Environment Setup(Jupyter notebook), Data Format Compatibility | Sai Rithin,Shiva,Kumar | 3- Completed
EDA - Analyze sales trends and customer behavior | 1 | 2 | Explore and visualize the sales and customer behavior trends in the dataset so as to identify key patterns, understand revenue drivers, and provide actionable insights. | SHOULD HAVE | Access to the required libraries/tools for data exploration and visualization (e.g., Pandas, Matplotlib, Seaborn, etc.), Cleaned and preprocessed dataset, | Sathvika,Sai Rithin,Arpan | 3- Completed
Feature Engineering - Create features for customer segmentation | 2 | 3 | Created meaningful features such as Recency, Frequency, and Monetary values for customer segmentation. This will help identify customer behavior patterns and build the foundation for clustering analysis | MUST HAVE | Cleaned dataset from Sprint 1, Understanding of customer behavior metrics (RFM), Pandas for feature computation | Sathvika | 3- Completed
Clustering Analysis - Segment customers with K-Means clustering | 2 | 4 | Segment customers into clusters using K-Means clustering on the generated RFM features to identify distinct customer groups for targeted marketing and strategic planning | MUST HAVE | Features created in the Feature Engineering task, tools like Scikit-learn for clustering, and visualization libraries like Matplotlib and Seaborn | Sathvika | 3- Completed
Model Building - Train a Random Forest model for sales prediction | 3 | 5 | Used RFM features to train a Random Forest Regressor Model. The features being Recency, Frequency and Cluster and target variable being Monetary. | MUST HAVE | Python libraries like Scikit-learn, Matplotlib and Seaborn. | Sai Rithin | 3- Completed
Model Evaluation - Validate model with RMSE and feature importance | 3 | 6 | Used Evaluation Metrics to evaluate the model created. Used MAE, RMSE and R-squared. Then found feature importances i.e. which feature is more important. | MUST HAVE | Evaluation metrics used from sklearn.metrics | Arpan | 3- Completed
Final Model Adjustment - Refine clustering and predictive model | 4 | 7 | alternative techniques used for better results, used hyperparametr tuning for better results | MUST HAVE | Dataset preprocessed and ready | Sai Rithin, Sathvika | 3- Completed
Business Recommendations - Summarize findings for strategic actions | 4 | 8 | detailed summary of findings for actionable recommendations | MUST HAVE | Finalized model evaluation | Sai Rithin, Sathvika, Arpan | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 7 | 2 | 1 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
7 | 401 | Optimize clustering parameters for better segmentation. | 2024-12-23 | 2024-12-23 | Rithin, Sathvika | Coding | 3- Completed | 2 | Day 1: 2
7 | 402 | Validate predictive model performance using RMSE and accuracy. | 2024-12-24 | 2024-12-24 | Rithin, Kumar | Coding | 3- Completed | 1 | bar: Day 2
7 | 403 | Recreate visualizations to represent feature importance and clusters. | 2024-12-26 | 2024-12-26 | Kumar, Rithin, Sathvika | Coding | 3- Completed | 1 | bar: Day 4
8 | 404 | Conduct impact analysis for actionable business recommendations. | 2024-12-27 | 2024-12-27 | Rithin, Sathvika, Arpan | Others | 3- Completed | 2 | Day 5: 2
8 | 405 | Draft the final summary report of findings and recommendations. | 2024-12-28 | 2024-12-28 | Rithin, Sathvika, Arpan | Others | 3- Completed | 1 | bar: Day 6

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint - 4 | Day 1 | Difficulty in fine-tuning clustering parameters for optimal grouping. | Reviewed clustering metrics (e.g., silhouette score) and adjusted hyperparameters.
Sprint - 4 | Day 2 | Predictive model refinement caused overfitting on training data. | Implemented regularization and cross-validation to address overfitting.
Sprint - 4 | Day 3 | Model accuracy problems | Adjusted the model to get favourable accuracy
Sprint - 4 | Day 4 | Summarizing findings into actionable business recommendations was time-consuming. | Focused on key insights.
Sprint - 4 | Day 5 | Summarizing findings into actionable business recommendations was time-consuming. | Focused on key insights and prioritized recommendations for immediate implementation.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint-1 | 2024-11-04 | 2024-11-22 | Sai Rithin, Sathvika, Arpan Kumar, Shiva | Much Involvement while presentation and testing | Overlapping sprint Goals | Having clear sprint goals | Perform testing after every successful task
2 | Sprint-2 | 2024-11-25 | 2024-12-06 | Sai Rithin, Sathvika, Arpan Kumar, Shiva | Much Involvement while presentation and testing | Overlapping sprint Goals | Having clear sprint goals | Perform testing after every successful task
3 | Sprint 3 | 2024-12-09 | 2024-12-20 | Sai Rithin, Sathvika, Arpan Kumar, Shiva | Much Involvement while presentation and testing | Overlapping sprint Goals | Having clear sprint goals | Perform testing after every successful task
4 | Sprint 4 | 2024-12-23 | 2024-12-27 | Sai Rithin, Sathvika, Arpan Kumar, Shiva | Much Involvement while presentation and testing | Overlapping sprint Goals | Having clear sprint goals | Perform testing after every successful task

## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Rithin | 2024-11-14 | Total Amount formula is wrong and it is derived column | Sprint-1 | Arpan | funtionality | Update with new formula | 2024-11-14 | closed | total amount is showed as expected
2 | Sathvika | 2024-11-19 | by mistake two dervied columns are added with same condition | Sprint-1 | Rithin | Data | removed that column | 2024-11-19 | closed | now data is fine
3 | Sathvika | 2024-11-27 | Incorrect monetary value calculation for some customers due to missing or invalid data in the Quantity or UnitPrice columns. | Sprint-2 | Rithin | Compatibility | Added data validation checks to handle missing or invalid values during feature engineering. Rows with null or negative values in Quantity or UnitPrice were excluded from the computation | 2024-11-29 | Closed | monetary value calculation corrected
4 | Rithin | 2024-11-30 | Discrepancy in Frequency calculation due to duplicate invoices for certain customers | Sprint-2 | Arpan | Data | Updated the logic to count unique InvoiceNo values for each customer while calculating Frequency, ensuring accurate metrics | 2024-12-02 | Closed | Results as expected
5 | Sathvika | 2024-12-03 | Normalized RFM values contained inconsistencies due to the presence of extreme outliers in the data | Sprint-2 | Arpan | Data | Applied log transformation to RFM metrics to mitigate the effect of outliers and re-scaled the data using MinMaxScaler | 2024-12-04 | Closed | consistency of normalized values maintained
6 | Rithin | 2024-12-04 | The Elbow Method visualization showed inconsistent results due to incorrect clustering initialization parameters. | Sprint-2 | Sathvika | funtionality | Adjusted the initialization parameters for K-Means clustering (e.g., random_state and n_init). Re-ran the Elbow Method analysis to ensure reliable results | 2024-12-05 | Closed | Elbow Method analysis corrected
7 | Sathvika | 2024-12-09 | Missing values detected in key features of the dataset. | Sprint-3 | Rithin | Data | Imputed missing values using mean/median for numerical features. | 2024-12-09 | Closed | Dataset ready for model training.
8 | Rithin | 2024-12-10 | Outliers causing skewness in the distribution of numerical variables. | Sprint-3 | Arpan | Data | Identified outliers using IQR; removed extreme values. | 2024-12-10 | Closed | Dataset normalized.
9 | Arpan | 2024-12-11 | High training time for Random Forest model due to large dataset size. | Sprint-3 | Rithin | integration | Subsampled dataset for faster iterations; optimized hyperparameters. | 2024-12-13 | Closed | Training time reduced by 30%.
10 | Rithin | 2024-12-16 | RMSE results varied significantly across cross-validation folds. | Sprint-3 | Sathvika | Usability | Increased number of folds and checked data distribution consistency. | 2024-12-18 | Closed | RMSE variance reduced.
11 | Sathvika | 2024-12-18 | Overfitting observed in Random Forest model after hyperparameter tuning. | Sprint-3 | Arpan | Usability | Reduced maximum depth and number of estimators to mitigate overfitting. | 2024-12-20 | Closed | Model generalized better on validation.
12 | Arpan | 2024-12-23 | Clustering parameters led to poor Silhouette score. | Sprint-4 | Rithin | funtionality | Tuned parameters and scaled features; used PCA for dimensionality reduction. | 2024-12-24 | Closed | Improved clustering performance.
13 | Kumar | 2024-12-24 | Predictive model showed overfitting during validation. | Sprint-4 | Arpan | integration | Reduced complexity of the model and added regularization techniques. | 2024-12-24 | Closed | Validation scores stabilized.
14 | Rithin | 2024-12-26 | Lack of clarity in visualizing feature contribution to clusters. | Sprint-4 | Sathvika | Compatibility | Used advanced visualizations with SHAP and clustering-specific charts. | 2024-12-26 | Closed | Feature contributions better understood.
15 | Sathvika | 2024-12-27 | Business recommendations lacked clear prioritization of findings. | Sprint-4 | Rithin | Usability | Conducted impact analysis and ranked insights based on business relevance. | 2024-12-27 | Closed | Recommendations now actionable.

## UT
Sl: No: | Test Case Name | Test Procedure | Condition to be tested | Expected Result | Actual Result
Random Forest Implementation
7 | Re-Validate clustering | use clustering techniques | customer segments | correct customer segments | successfully re-validated clustering
8 | Re-Validate Model Training | Train the random forest model with sample data. | Predictions are in suitable range | All predicted probabilities fall within the valid range | tested the trained model using the testing data. gave all predicted probabilities within the valid range
9 | Validate Performance Metrics | Compute MAE, RMSE, R-squared | Metrics align with expected values for sample data | Metrics match expected values | computed MAE, RMSE and R^2 to evaluate the trained model. all the evaluation metrics tell that the accuracy og the trained model is good